## Dashboard
System Engineer Roadmap: Progress Dashboard
Premier System ¦ Red Hat + VMware ¦ 4-month plan from trainee to client-ready engineer
Start Date | 2026-10-07 | Assumption: set to the date this plan was made. Change to your actual start date.
Planned End | 2027-01-27
Current Week | 1
Time Elapsed | 1.786%
Tasks Completed | 0
Total Tasks | 53
Overall Completion | 0%
Schedule Status | Behind schedule
Hours Studied (Weekly Review) | 0
Lab Log Hours | 1.5
Certifications Passed | 0
Progress by Month
Month | Theme | Tasks | Done | Completion %
1 | Foundations | 15 | 0 | 0%
2 | VMware Track | 13 | 0 | 0%
3 | Red Hat Track | 13 | 0 | 0%
4 | Solutions & Certification | 12 | 0 | 0%
Progress by Task Type
Type |  | Tasks | Done | Completion %
Theory |  | 26 | 0 | 0%
Lab |  | 21 | 0 | 0%
Milestone |  | 6 | 0 | 0%
How to use
1. Weekly Plan: change Status (dropdown) as you work. Blue cells are yours to edit.
2. Weekly Review: log hours and a 1-5 self-score every Friday.
3. Lab Log: record each problem and fix; row 5 is an example to overwrite.
4. Certifications: update status and score as you book and pass exams.
5. Yellow cell above (Start Date) drives Current Week and On track / Behind.

## Weekly Plan
Weekly Plan & Checklist
Set Status to Done as you finish each task. Everything on the Dashboard updates automatically.
ID | Month | Week | Track | Task | Type | Status | Date Done | Notes
1 | 1 | 1 | Linux Foundations | Command line, users, groups, permissions, ownership | Theory | Not Started
2 | 1 | 1 | Linux Foundations | systemd services and package management (dnf/rpm) | Theory | Not Started
3 | 1 | 1 | Linux Foundations | Build a RHEL VM with static IP and SSH hardening | Lab | Not Started
4 | 1 | 2 | Linux Foundations | LVM, file systems, mounting, RAID basics | Theory | Not Started
5 | 1 | 2 | Linux Foundations | Create, extend and shrink LVM volumes in a lab VM | Lab | Not Started
6 | 1 | 2 | Linux Foundations | Networking: IP, DNS, firewalld, NIC bonding | Theory | Not Started
7 | 1 | 3 | Networking | Datacenter networking: VLANs, trunks, LACP, MTU | Theory | Not Started
8 | 1 | 3 | Networking | Configure VLAN and bond on RHEL | Lab | Not Started
9 | 1 | 3 | Linux Foundations | Bash scripting basics: variables, loops, conditions | Theory | Not Started
10 | 1 | 3 | Linux Foundations | Write a script that audits users, disk and services | Lab | Not Started
11 | 1 | 4 | Hardware & Storage | Virtualization concepts: hypervisor, cluster, HA, live migration | Theory | Not Started
12 | 1 | 4 | Hardware & Storage | Storage: SAN vs NAS, iSCSI, Fibre Channel, RAID levels, IOPS | Theory | Not Started
13 | 1 | 4 | Hardware & Storage | HPE iLO and Dell iDRAC; firmware and RAID controllers | Theory | Not Started
14 | 1 | 4 | Hardware & Storage | Processors (Intel Xeon gens, AMD EPYC) and GPU servers (NVIDIA H200) | Theory | Not Started
15 | 1 | 4 | Hardware & Storage | MILESTONE: Month 1 review with mentor | Milestone | Not Started
16 | 2 | 5 | VMware vSphere | ESXi and vCenter installation (nested lab) | Lab | Not Started
17 | 2 | 5 | VMware vSphere | Datastores, VM templates and cloning | Lab | Not Started
18 | 2 | 5 | VMware vSphere | Virtual networking: vSwitch, port groups, VLANs | Theory | Not Started
19 | 2 | 6 | VMware vSphere | Clusters: HA, DRS, resource pools | Theory | Not Started
20 | 2 | 6 | VMware vSphere | vMotion: migrate a VM live between hosts | Lab | Not Started
21 | 2 | 6 | VMware vSphere | Snapshots, backups and restore basics | Lab | Not Started
22 | 2 | 7 | VMware vSAN | vSAN architecture and storage policies | Theory | Not Started
23 | 2 | 7 | VMware vSAN | Build a vSAN cluster in the lab | Lab | Not Started
24 | 2 | 7 | VMware vSAN | Fail a host or disk and observe vSAN behaviour | Lab | Not Started
25 | 2 | 8 | VMware NSX & VCF | NSX segments, gateways and distributed firewall | Lab | Not Started
26 | 2 | 8 | VMware NSX & VCF | VMware Cloud Foundation (VCF) architecture overview | Theory | Not Started
27 | 2 | 8 | VMware vSphere | Lifecycle Manager patching and monitoring | Lab | Not Started
28 | 2 | 8 | VMware vSphere | MILESTONE: Document full vSphere + vSAN lab build | Milestone | Not Started
29 | 3 | 9 | Red Hat RHEL | RHCSA objectives: users, storage, SELinux, boot process | Theory | Not Started
30 | 3 | 9 | Red Hat RHEL | Practice RHCSA-style tasks under time limit | Lab | Not Started
31 | 3 | 9 | Red Hat RHEL | Networking, firewalld and SELinux troubleshooting | Lab | Not Started
32 | 3 | 10 | Red Hat Ansible | Ansible basics: inventory, ad-hoc commands, playbooks | Theory | Not Started
33 | 3 | 10 | Red Hat Ansible | Roles, variables and templates | Theory | Not Started
34 | 3 | 10 | Red Hat Ansible | Automate a full server build with a playbook | Lab | Not Started
35 | 3 | 11 | Containers | Podman: images, containers, volumes, registries | Lab | Not Started
36 | 3 | 11 | Containers | Kubernetes concepts: pods, deployments, services | Theory | Not Started
37 | 3 | 11 | Containers | Run a multi-container application | Lab | Not Started
38 | 3 | 12 | Red Hat OpenShift | OpenShift architecture, projects, routes, storage, operators | Theory | Not Started
39 | 3 | 12 | Red Hat OpenShift | Deploy a small cluster or OpenShift Local and an app | Lab | Not Started
40 | 3 | 12 | Morpheus | Morpheus cloud management platform: overview and demo | Theory | Not Started
41 | 3 | 12 | Red Hat OpenShift | MILESTONE: App on OpenShift automated with Ansible | Milestone | Not Started
42 | 4 | 13 | Solution Design | Customer decision path: containers + virtualization (Red Hat) vs virtualization only (VMware) | Theory | Not Started
43 | 4 | 13 | Solution Design | Discovery questions: workloads, growth, budget, skills | Theory | Not Started
44 | 4 | 13 | Solution Design | Sizing: CPU, RAM, storage (e.g. 50 TB to 75 TB SAN), licensing editions | Theory | Not Started
45 | 4 | 14 | Solution Design | External SAN, backup and DR design | Theory | Not Started
46 | 4 | 14 | Solution Design | HPE and Dell server and storage portfolio: what to quote when | Theory | Not Started
47 | 4 | 14 | Solution Design | GPU and AI workload basics | Theory | Not Started
48 | 4 | 15 | Capstone | Write BOM and architecture diagram for fictional customer | Lab | Not Started
49 | 4 | 15 | Capstone | Write HLD (high-level design) document | Lab | Not Started
50 | 4 | 15 | Capstone | Build 10-slide solution presentation | Lab | Not Started
51 | 4 | 16 | Certification | Sit certification exam (RHCSA or VCP) | Milestone | Not Started
52 | 4 | 16 | Capstone | Present capstone to manager / senior engineer | Milestone | Not Started
53 | 4 | 16 | Capstone | MILESTONE: Final 4-month review and next 90-day plan | Milestone | Not Started

## Weekly Review
Weekly Review
Task counts come from Weekly Plan. Fill in the blue cells at the end of each week (30 min with your mentor).
Week | Month | Tasks | Done | Completion % | Hours Studied | Self-Score (1-5) | Wins / Blockers / Next Week Goal
1 | 1 | 3 | 0 | 0%
2 | 1 | 3 | 0 | 0%
3 | 1 | 4 | 0 | 0%
4 | 1 | 5 | 0 | 0%
5 | 2 | 3 | 0 | 0%
6 | 2 | 3 | 0 | 0%
7 | 2 | 3 | 0 | 0%
8 | 2 | 4 | 0 | 0%
9 | 3 | 3 | 0 | 0%
10 | 3 | 3 | 0 | 0%
11 | 3 | 3 | 0 | 0%
12 | 3 | 4 | 0 | 0%
13 | 4 | 3 | 0 | 0%
14 | 4 | 3 | 0 | 0%
15 | 4 | 3 | 0 | 0%
16 | 4 | 3 | 0 | 0%
Total |  | 53 | 0 | 0% | 0 | 0

## Certifications
Certification Tracker
Check vendor sites for current exam codes and prices; Broadcom/VMware has changed its program recently.
Certification | Vendor | Priority | Target Date | Status | Score / Result | Notes
RHCSA (EX200) | Red Hat | Primary | Week 16 | Not Started |  | Practice with timed labs in Week 9.
VCP (VMware Certified Professional, current VCF/vSphere track) | VMware / Broadcom | Primary | Week 16 | Not Started |  | Verify exam code and prerequisites on Broadcom's site.
RHCE / OpenShift Administration | Red Hat | Stretch | After Month 4 | Not Started |  | Plan for the next 90 days.
HPE / Dell partner training | HPE / Dell | Supporting | Ongoing | Not Started |  | Ask Premier System about partner-portal access.

## Lab Log
Lab Log & Runbook
Write down every issue you solve. This becomes your personal knowledge base. The first row is an example; overwrite it.
Date | Week | Topic | Problem / What I Did | Fix / Learning | Hours
2026-10-12 | 1 | RHEL networking | VM had no network after cloning | Regenerated machine-id and fixed NIC name in nmcli | 1.5