## Pre-Bid Queries
PRE-BID QUERIES – PROCUREMENT OF GPU SERVERS FOR ICT DTE NUST H-12 CAMPUS ISLAMABAD (Tender Ref: P158775)
Submitted by: Premier Systems (Pvt) Ltd ¦ Procuring Agency: NUST (P&LP), P&LP Dte, NUST H-12 ¦ Pre-bid meeting: Mon 26 Oct 2026, 02:30 PM ¦ Clarification deadline (EPADS): Mon 2 Nov 2026 ¦ Bid submission: Thu 5 Nov 2026, 11:00 AM
Legend: yellow columns = RFP page and clause reference; green column = to be filled by NUST. Page numbers follow the RFP footer 'Page X of 85' (PDF viewer page = printed page + 2).
S. No | Section | RFP Page No. (as printed) | Clause / Reference | RFP Provision (as stated) | Query / Clarification Sought | Category | Priority | NUST Response
14 | Evaluation | 32-33 | Evaluation Criteria – Accelerator vendor partnership (5 marks) | NVIDIA Partner Network or equivalent: Elite (5), Preferred (3), Registered/member (1). | Please confirm whether the bidder's own NPN status is required, or whether the server OEM's or distributor's NVIDIA status may be considered. Is a specific NPN competency (e.g. Compute / AI infrastructure) required? | Evaluation | Medium
23 | Schedule | 37, 40, 46 | Items/Lots; Option-1 Ser 3; Option-2 Ser 3 | Data-centre GPUs (RTX PRO 6000 Blackwell Server Edition / H200 NVL) to be new, genuine and supplied via OEM channel. | Data-centre GPUs are subject to US export regulations and long OEM lead times. Will NUST provide an End-User / End-Use Certificate when required by the OEM? Please confirm that delays caused by export-licence processing beyond the bidder's control will be treated as excusable delay (no liquidated damages), and consider a delivery period of 90-120 days. | Schedule | High
24 | Schedule | 37, 43, 50 | Items/Lots – Delivery address; Section-2 Ser 1 | Delivery address: P&LP Dte, Near NUST MT Area. Installation: 'existing data centre'. | Please confirm the installation site (ICT Dte data centre location) and whether goods are to be delivered directly to the data centre rather than to P&LP Dte. | Schedule | Low
25 | Commercial | 27, 30, 64 | BDS 9 (ITB 16.1); Eligibility Criteria Row 4; GCC 36 | Prices in PKR; payment after deduction of income tax and part of sales tax; supplier responsible for taxes until delivery. | Please confirm that quoted prices shall be inclusive of all applicable taxes (GST on goods and ICT/provincial sales tax on services) and the withholding rates NUST will apply. Should taxes be shown separately in the price schedule? | Commercial | High
26 | Commercial | 52 | Price Schedule | One line per item (Unit Price / Total Price). Spec (Section 1 Ser 6) requires bidders to itemize each chargeable subscription. | May bidders attach a detailed itemized BOQ (hardware, software subscriptions, services) with the financial bid, with the EPADS price schedule carrying the total per option? Which prevails in case of discrepancy? | Commercial | Medium
27 | Commercial | 11, 27 | ITB 15.6; BDS 8 | Prices fixed; adjustable price bids rejected. | Given that hardware and subscriptions are USD-denominated and imported, will NUST consider an exchange-rate variation clause if PKR/USD moves beyond a set band (e.g. ±3%) between bid submission and LC/payment? | Commercial | Medium
28 | Commercial | 63, 68 | GCC 32; SCC (GC Clause 32) | Payment 'according to the actual invoice or running bills ... within the time given in the conditions of the contract'. No milestones or payment period stated. | Please specify payment milestones and the payment period. We propose: 70% on delivery and inspection, 30% on installation, commissioning and acceptance, payable within 30 days of invoice. Is advance payment against a bank guarantee possible? | Commercial | High
29 | Commercial | 61-62, 68 | GCC 23; SCC (GC Clause 23) | Performance guarantee 5% of contract price as Pay Order; discharged 30 days after completion of performance obligations including warranty (GCC 23.5). | (a) Is a bank guarantee acceptable instead of a Pay Order? (b) Since GCC 23.5 links release to warranty completion, the 5% would be held for 3 years. Please confirm release on acceptance, or allow conversion to a warranty bank guarantee. (c) GCC 23.6 states the bid security shall not be substituted with the Performance Guarantee; please confirm when the successful bidder's bid security will be returned (ITB 18.8). | Commercial | Medium
35 | Technical – Site | 39, 43, 45 | Option-1 Ser 1; Option-2 Ser 1; Section-2 Ser 1 | Racking into existing hot/cold-aisle data centre; blanking panels to be provided. | Please share: rack make/model and usable depth (mm), available rack units, power available per rack (kW), PDU make and outlet type (C13/C19), and whether A/B feeds are on separate UPS. A 4 x 600 W GPU server can draw roughly 3.5-4.5 kW; please confirm the rack can support this. | Technical | High
36 | Technical – Site | 45 | Option-2 Ser 1 (also relevant to Option-1) | Bidder to state OEM-supported maximum inlet (cold-aisle) temperature. | Please share the current cold-aisle supply temperature and humidity in NUST's data centre so that the offered configuration can be validated by the OEM for continuous full-TDP operation. | Technical | Medium
37 | Technical – Site | 41, 47 | Option-1 Ser 8; Option-2 Ser 8 (Power supplies) | Minimum N+1 PSU redundancy at full load; design shall support independent A and B feeds. | N+1 and A/B feed redundancy are different requirements. With A/B feeds, losing one feed removes half the PSUs, which requires N+N (grid) redundancy. Please confirm whether N+1 is sufficient, or whether full-load operation on a single feed (N+N) is required. | Technical | High
38 | Technical – Hardware | 39, 45 | Option-1 Ser 1; Option-2 Ser 1 | Dual Intel Xeon 6 or 5th Gen Xeon Scalable, minimum 48 physical cores each. | Will AMD EPYC 9004/9005 processors with equal or higher core count be accepted as equivalent? Many OEM-certified GPU platforms are offered on both, and allowing either would increase competition. | Technical | Medium
39 | Technical – Hardware | 40, 45 | Option-1 Ser 2 (Qty 32, '64 Gb x 32'); Option-2 Ser 2 | Minimum 2 TB DDR5 ECC RDIMM 'operating at 4800 MT/s or higher', module size/count not restricted. | On 5th Gen Xeon (8 channels/socket), 32 DIMMs means 2 DIMMs per channel, which runs at 4400 MT/s. On Xeon 6 (12-channel) platforms, 2 TB requires different module sizes (e.g. 16 x 128 GB). Please confirm whether 4800 MT/s refers to the module rated speed or the operating speed at the configured population, and that any OEM-recommended configuration of ≥2 TB is acceptable regardless of the '64 GB x 32' description. | Technical | High
40 | Technical – Hardware | 39-40 | Option-1 Ser 1 & Ser 3 | Option-2 chassis must be listed as NVIDIA-Certified; Option-1 only requires 'factory-integrated or formally validated' by the OEM. | For Option-1, is listing as an NVIDIA-Certified System for the RTX PRO 6000 Blackwell Server Edition required, or is OEM validation sufficient? | Technical | Medium
41 | Technical – Hardware | 40 | Option-1 Ser 3 (GPU) | 4 GPUs equal to or better than RTX PRO 6000 Blackwell Server Edition; support for MIG. | (a) RTX PRO 6000 Server Edition has no NVLink; please confirm GPU-to-GPU communication over PCIe Gen5 is acceptable for Option-1. (b) What MIG partitioning is expected per GPU? (c) Please confirm whether non-NVIDIA accelerators will be evaluated as 'equivalent' and on what benchmark basis. | Technical | Medium
42 | Technical – Hardware | 40, 46 | Option-1 Ser 4; Option-2 Ser 4 (Storage) | ≥20 TB usable NVMe after data protection; ≥25% vacant and 'enabled' bays; ≥1 DWPD. | (a) Please confirm 'enabled' means bays cabled to backplane/controller and usable without additional purchase. (b) Is there a preferred RAID level for data (RAID 5/6/10)? (c) Is software RAID (e.g. Intel VROC) acceptable versus a hardware tri-mode controller? (d) What is the minimum capacity for the mirrored boot drives? | Technical | Medium
43 | Technical – Hardware | 41, 47 | Option-1 Ser 6; Option-2 Ser 6 (25GbE) | Minimum two 25GbE SFP28 ports; compatible optics or DAC/AOC to be included. | Please share the make/model of the upstream switch, whether free 25G ports are available, the distance to the switch (to size DAC/AOC vs SR optics), and confirm that switch-side configuration (VLANs, LACP, RoCE/PFC) will be done by NUST or is in the bidder's scope. | Technical | Medium
45 | Technical – Hardware | 41, 48 | Option-1 Ser 10; Option-2 Ser 10 (Warranty) | Repair and maintenance within warranty, 24x7 with Next Business Day onsite response, 3 years. | Please clarify '24x7 with NBD': is 24x7 call logging with NBD onsite acceptable, or is 24x7 4-hour onsite required? Is defective-media / keep-your-drive retention required for failed NVMe drives? | Technical | Medium
46 | Technical – Software | 42, 48 | Option-1 & Option-2 Section 1 Ser 1 (NVIDIA AI Enterprise) | Option-2 text states subscription 'covering all four offered accelerators' although Option-2 has two GPUs. | Please confirm the Option-2 NVAIE requirement is for 2 GPUs (typographical error). Also, H200 NVL normally includes a bundled NVAIE subscription; please confirm a bundled subscription registered to NUST satisfies this item. | Technical | High
47 | Technical – Software | 42 | Option-1 Section 1 Ser 1 | NVIDIA AI Enterprise for all four RTX PRO 6000 GPUs for three years. | Please confirm the required edition (NVIDIA AI Enterprise full subscription vs Essentials) and that per-GPU 3-year subscriptions with Business Standard support are acceptable. | Technical | Medium
48 | Technical – Software | 42, 48 | Section 1 Ser 2 (Enterprise Linux) | RHEL, Ubuntu Pro, SLES, Rocky Linux with support, or equivalent. | Does NUST have a preferred distribution or existing enterprise agreement (e.g. RHEL)? If Kubernetes nodes / control-plane VMs also need OS subscriptions, how many instances should be priced? | Technical | Medium
49 | Technical – Software | 42, 49 | Section 1 Ser 3 (Monitoring) | Integration with the Purchaser's existing monitoring environment shall be included. | Please specify the existing monitoring platform(s) and versions (e.g. Zabbix, Prometheus/Grafana, PRTG, SolarWinds, vRealize/Aria) to define the integration scope. | Technical | Medium
50 | Technical – Software | 43, 49 | Section 1 Ser 5 (Container orchestration) | Enterprise-supported Kubernetes / OpenShift / CNCF-conformant platform; control plane virtualized on existing estate. | (a) Is a paid enterprise subscription (OpenShift, Rancher Prime, etc.) mandatory, or is upstream Kubernetes with bidder support for 3 years acceptable? (b) Will NUST provide the VMs (vCPU/RAM/storage), hypervisor licences and OS for the control plane on VMware/Sangfor, and how many control-plane nodes are expected (1 or 3 for HA)? | Technical | High
51 | Services | 43, 50 | Section-2 Ser 2 (VMware & Sangfor integration) | Integration for control-plane tier: network, VLAN, DNS, NTP, identity and monitoring. | Please share VMware vSphere and Sangfor HCI versions, identity source (AD/LDAP/Entra ID), and confirm that NUST will provide administrative access and IP/VLAN allocations. | Services | Medium
52 | Services | 44, 50 | Section-2 Ser 3 (LLM inference & RAG) | Deploy vLLM / TensorRT-LLM with OpenAI-compatible API, plus embedding model, reranker, vector database and ingestion workers. | Please specify: (a) target LLM(s) and sizes (e.g. 70B, quantization), (b) expected concurrent users / throughput, (c) preferred vector database, (d) document sources and volume for ingestion, (e) whether a user-facing chat UI or application development is in scope, and (f) that model weights will be open-weight models whose licence terms are accepted by NUST. | Services | High
53 | Services | 44, 50 | Section-2 Ser 4 (Migration) | Migration of existing AI/ML workloads, including container images, model weights and datasets. | Please provide an inventory of existing workloads: number of workloads, current platform, total data volume (TB), downtime windows, and whether application re-engineering is expected. Without this, we request that migration be limited to a defined number of workloads/data volume. | Services | High
55 | Services | 44, 50 | Section-2 Ser 6 (Training and certification) | Onsite/virtual knowledge transfer; training material and certificates to be provided. | Please specify the number of participants and training days. Please confirm 'certificates' means training completion certificates issued by the bidder/OEM, not vendor certification exam vouchers (e.g. NVIDIA, Red Hat). | Services | Medium

## Summary
Query Summary
Category | Total | High | Medium | Low
Bid Security | 0 | 0 | 0 | 0
Submission | 0 | 0 | 0 | 0
Evaluation | 1 | 0 | 1 | 0
Schedule | 2 | 1 | 0 | 1
Commercial | 5 | 2 | 3 | 0
Contractual | 0 | 0 | 0 | 0
Technical | 15 | 5 | 10 | 0
Services | 4 | 2 | 2 | 0
Total | 27 | 10 | 16 | 1
Answered by NUST | 0